## Sheet1
Grant Chart: Smart Home Automation System (Updated)
This updated Grant Chart reflects the project's progress starting from December 1st, 2024, to the present day.
Task | Start Date | End Date | Duration | Resources | Dependencies | Status
Project Planning & Design | 2024-12-01 | 2024-12-02 | 1 day | Project Manager, Team Members |  | Completed
Hardware Procurement | 2024-12-02 | 2024-12-07 | 5 days | Project Manager |  | Completed
Circuit Design & Schematic | 2024-12-03 | 2024-12-12 | 9 days | Developers | Hardware Procurement | Completed
Code Development (Sensor Reading & Logic) | 2024-12-05 | 2024-12-10 | 5 days | Developer | Circuit Design & Schematic | Completed
Code Development (Servo Control) | 2024-12-06 | 2024-12-10 | 4 days | Developer/Project Leader | Code Development (Sensor Reading & Logic) | Completed
Assembly & Testing (Initial) | 2024-12-10 | 2024-12-13 | 3 days | Project Manager, Developer, Quality Assurance | Hardware Procurement, Code Development (Servo Control) | Completed
Calibration & Optimization | 2024-12-11 | 2024-12-13 | 1 day | Project Manager, Developer, Quality Assurance | Assembly & Testing (Initial) | In Progress
Documentation & User Manual | 2024-12-01 | 2024-12-13 | 12 days | Project Manager, Developer, Quality Assurance | Assembly & Testing (Initial) | On Hold
Final Testing & Demonstration | 2024-12-12 | 2024-12-13 | 1 day | Project Manager, Developer, Quality Assurance | Calibration & Optimization, Documentation & User Manual | On Hold